## Summary
THE TASTE OF ANDHRA — ADMIN PERSONA QA
Persona | Admin
Tested on | 2026-07-27
Environment | Local (http://127.0.0.1:5173)
Credentials | admin@tasteofandhra.test
Total tested | 33
Pass | 22
Fail | 8
Blocked / Not fully exercised | 3
NOT WORKING (FAIL) — details also in Not Working sheet
1. Delivery Partners CRUD page | Missing Supabase table public.delivery_partners — migration not applied.
2. Branches management | Missing Supabase table public.branches — future_features migration not applied.
3. QR Tables management | Missing Supabase table public.qr_tables (depends on branches migration).
4. Save Default ETA in Settings | Missing Supabase table public.app_settings.
5. Persist Delivery & Service Area settings | Missing Supabase table public.delivery_settings.
6. Service area RPC check | Missing DB function public.check_delivery_service_area.
7. Partner live GPS tracking | Partners not sharing GPS; Track shows 'Partner not sharing GPS'.
8. Pidge Edge Function / live delivery quote | Edge Function request failed; falls back to rate card.

## Functionalities Tested
ID | Area | Functionality | Steps | Expected | Status | Evidence / Notes | Tester Sign-off
ADM-01 | Authentication | Admin login | Open /admin/login → fill demo admin credentials → Sign In to Admin | Redirect to /admin dashboard | Pass | Login succeeded; landed on Dashboard with stats.
ADM-02 | Authentication | Admin route guard (unauthenticated) | Visit protected admin URL without session | Redirect to /admin/login | Pass | After session loss, protected URL redirected to /admin/login.
ADM-03 | Dashboard | Dashboard stats & recent orders | Open /admin | Shows total orders, revenue, customers, popular dish, recent orders | Pass | Total Orders 9, Revenue ₹6,467, Customers 9, Popular Dish Gongura Mutton Biryani.
ADM-04 | Dashboard | Quick links to admin sections | View Manage Restaurant links on dashboard | Links to Categories, Dishes, Orders, Customers, Offers, Reports | Pass | Quick links rendered and navigable.
ADM-10 | Categories | List categories | Open /admin/categories | Categories table loads | Pass | Starters, Biryani, Curries, Breads, Beverages listed.
ADM-11 | Categories | Create category | Add Category → name 'QA Test Category' → Create | Category appears as Active | Pass | Created with slug qa-test-category.
ADM-12 | Categories | Soft-delete category | Delete QA Test Category → confirm | Category deactivated (Inactive) | Pass | Status changed to Inactive.
ADM-13 | Categories | Edit category / image upload UI | Open Add/Edit modal | Form fields including image upload available | Pass | Modal fields present. File upload not end-to-end tested.
ADM-14 | Dishes | List dishes | Open /admin/dishes | Dishes table with prices/availability | Pass | 8 dishes listed.
ADM-15 | Dishes | Add Dish modal | Click Add Dish | Modal opens with required fields | Pass | Name, Category, Price, Spice, Description, etc. present.
ADM-16 | Dishes | Create/Edit/Delete dish (full save) | Create a new dish and save | Dish persists and appears on menu | Blocked | List + modal verified; full create not executed to avoid polluting live menu.
ADM-20 | Orders | Kitchen board list | Open /admin/orders | Board columns by status with live orders | Pass | Board/List toggle, filters, Delayed/Mute present.
ADM-21 | Orders | Update order status | Mark Ready on TOA-20260722-5820 | Order moves to Ready column | Pass | Moved from Preparing to Ready.
ADM-22 | Orders | ETA bump controls | View +10/+15/+20/Set buttons | ETA controls visible per order | Pass | Controls present; bump save not separately verified.
ADM-23 | Orders | Order detail view button | Confirm View order buttons exist | Detail action available | Pass | View TOA-… buttons present on board cards.
ADM-24 | Delivery | Awaiting assignment & active deliveries | Open /admin/delivery | Shows awaiting queue and active deliveries | Pass | Ready order in Awaiting Assignment; active deliveries with Track.
ADM-25 | Delivery | Assign Delivery Partner modal | Click Assign on awaiting order | Modal opens with partner list | Pass | Partners from delivery-role profiles listed. Submit not completed.
ADM-26 | Delivery | Live GPS tracking for partners | Expand Track on active deliveries | Partner GPS location shown | Fail | UI shows 'Partner not sharing GPS'.
ADM-27 | Delivery Partners | List / CRUD delivery partners | Open /admin/delivery-partners | Partner list loads | Fail | Unable to load delivery partners. Missing table public.delivery_partners (PGRST205). Migration not applied.
ADM-30 | Customers | List customers | Open /admin/customers | Customer list with Deactivate actions | Pass | 9 customers listed.
ADM-31 | Customers | Deactivate / reactivate customer | Toggle customer is_active | Status updates; login blocked when inactive | Blocked | UI present; not executed on live customer accounts.
ADM-33 | Offers | List offers | Open /admin/offers | Offers/coupons listed | Pass | 6 offers including test coupons.
ADM-34 | Offers | Add Offer modal | Click Add Offer | Form modal opens | Pass | Title, Discount, Coupon Code, dates present.
ADM-35 | Party Inquiries | List party inquiries | Open /admin/party-inquiries | Page loads; inquiries or empty state | Pass | Empty state shown; table exists with 0 rows.
ADM-36 | Party Inquiries | Update inquiry status | Change status on an inquiry | Status saved | Blocked | No inquiry records available.
ADM-40 | Branches | List / manage branches | Open /admin/branches | Branches load | Fail | Unable to load branches. Missing table public.branches (PGRST205).
ADM-41 | QR Tables | List / create QR tables | Open /admin/qr-tables | QR tables load | Fail | Unable to load QR tables. Missing table public.qr_tables (PGRST205).
ADM-37 | Reports | Sales reports & popular dishes | Open /admin/reports | Revenue, sales breakdown, charts | Pass | Revenue ₹6,467 from 9 orders; charts rendered.
ADM-38 | Settings | View settings page | Open /admin/settings | Restaurant info, pricing, delivery settings | Pass | Page loads with ETA, restaurant info, pricing, service area panel.
ADM-39 | Settings | Save default ETA (app_settings) | Change Default ETA → Save | ETA persisted in app_settings | Fail | Missing table public.app_settings (PGRST205). Load falls back; save cannot persist.
ADM-42 | Settings | Persist delivery_settings | Save delivery provider / service area | Settings stored in delivery_settings | Fail | Missing table public.delivery_settings (PGRST205). UI shows defaults only.
ADM-43 | Delivery infra | check_delivery_service_area RPC | Invoke service-area RPC | Function exists and returns result | Fail | Missing function public.check_delivery_service_area (PGRST202).
ADM-44 | Delivery infra | Pidge / delivery-quote Edge Function | Observed during delivery features | Edge function reachable or clean fallback | Fail | Failed to send request to Edge Function; falls back to rate card.

## Not Working
# | Functionality | Reason | Severity | Suggested Fix
1 | Delivery Partners CRUD page | Missing Supabase table public.delivery_partners — migration not applied. | High | Apply migration supabase/migrations/20250722100000_delivery_partners.sql
2 | Branches management | Missing Supabase table public.branches — future_features migration not applied. | High | Apply migration supabase/migrations/20250721200000_future_features.sql
3 | QR Tables management | Missing Supabase table public.qr_tables (depends on branches migration). | High | Apply future_features migration (creates qr_tables + branches)
4 | Save Default ETA in Settings | Missing Supabase table public.app_settings. | High | Apply migration that creates app_settings
5 | Persist Delivery & Service Area settings | Missing Supabase table public.delivery_settings. | High | Apply migration that creates delivery_settings
6 | Service area RPC check | Missing DB function public.check_delivery_service_area. | High | Apply SQL that creates check_delivery_service_area function
7 | Partner live GPS tracking | Partners not sharing GPS; Track shows 'Partner not sharing GPS'. | Medium | Require delivery partners to enable location sharing / verify GPS update path
8 | Pidge Edge Function / live delivery quote | Edge Function request failed; falls back to rate card. | Medium | Deploy and configure Supabase Edge Function delivery-quote + Pidge secrets